## Sheet1
section | completed | Description | Issues: | TODO | Assigned to
2.1.1 | PARTIAL | Login form, Email, password, and submission | No Error message, No auth check | implem auth check, implem error message, Add logout button in header | Ariq
2.1.2 | PARTIAL | Registration | No Error message, No auth check | implem auth check, implem error message | Ariq
2.1.3 | PARTIAL | Error popup for frontend | Bruh what do we use, Modal? | Implem with Modal | Ariq
2.2.1 | PARTIAL | Basic Feed |  | Integrate with hooks, frontend needs to be id based, change it so that small images get scaled up | Steven
Milestone 3 Advanced Feed
2.3.1 | PARTIAL | Show like on a job | Needs data to be inserted, frontend done | make it so that when you like a post, it stays red | Steven
2.3.2 | PARTIAL | show comments |  |  | Steven
2.3.3 | PARTIAL | liking a job |  |  | Steven
2.3.4 | PARTIAL | Feed Pagination |  | gnna do infinite scroll | Steven
Milestone 4: Other users and profiles
2.4.1 | PARTIAL | Viewing other's profiles, click on pfp to go to user page, display all jobs made by that person (no comments/likes), display all other users that they are watched by (modal) |  | implement link from profile pic | Ariq
2.4.2 | PARTIAL | Viewing your own profile, profile button on navbar |  |  | Ariq
2.4.3 | PARTIAL | Updating profile, Update profile: Email, Password, Name and Image |  | placeholders should be their old data | Ariq
2.4.4 | PARTIAL | Watching/Unwatching, unwatch button, watch button, email address popup to watch certain user |  |  | Ariq
Milestone 5: Adding and Updating Content
2.5.1 | PARTIAL | Adding a job, users can upload new content from a modal in the Home page
2.5.2 | PARTIAL | Updating and deleting a job |  | Implement frontend deletion, Edit Button for jobs
2.5.3 | PARTIAL | Comments |  | style changes for commetns required
Milestone 6: Challenge Components
2.6.1 | NO | Infinite Scroll (Home Page)
2.6.2 | NO | Live Update (Likes and comments are updated without refreshing page)
2.6.3 | NO | Push Notifications
Milestone 7: Very Challenging Components
2.7.1 | NO | Static Feed Offline access, | Stuff from job feed is still there but no erros for when user is offline | errors for when offline
OTHER